## Simple Gantt Chart - EX
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Leon W | 2023-03-12 | 2023-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2023-03-15 | 2023-03-16 | 1 | 100%
1.2 | Research | Pete S | 2023-03-15 | 2023-03-21 | 6 | 90%
1.3 | Projections | Steve L | 2023-03-16 | 2023-03-22 | 6 | 40%
1.4 | Stakeholders | Allen W | 2023-03-17 | 2023-03-22 | 5 | 70%
1.5 | Guidelines | Malik M | 2023-03-18 | 2023-03-22 | 4 | 60%
1.6 | Project Initiation | Malik M | 2023-03-23 | 2023-03-23 |  | 50%
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Steve L | 2023-03-24 | 2023-03-28 | 4 | 5%
2.2 | Budget | Allen W | 2023-03-29 | 2023-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  |  | 0%
2.4 | Risk Management | Malik M |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status and Tracking | Pete S |  |  |  | 0%
3.2 | KPIs | Leon W |  |  |  | 0%
3.2.1 | Monitoring | Kylie R |  |  |  | 0%
3.2.2 | Forecasts | Kylie R |  |  |  | 0%
3.3 | Project Updates | Pete S |  |  |  | 0%
3.3.1 | Chart Updates | Malik M |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  |  | 0%
4.2 | Quality Deliverables | Allen W |  |  |  | 0%
4.3 | Effort and Cost Tracking | Malik M |  |  |  | 0%
4.4 | Project Performance | Malik M |  |  |  | 0%

## Simple Gantt Chart - BLANK
GANTT CHART KELOMPOK VII
PROJECT TITLE | Sistem Informasi Rating Sekolah SMA Favorit di Kota Jayapura Berbasis Website
PROJECT MANAGER | Vika Indi Ramadhani
COMPANY NAME | Kelompok 7
Project Start | 2025-03-17
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | 2025-03-17 |  |  |  |  | 2025-03-24 |  |  |  |  | 2025-03-31 |  |  |  |  | 2025-04-07 |  |  |  |  | 2025-04-14 |  |  |  |  | 2025-04-21 |  |  |  |  | 2025-04-28 |  |  |  |  | 2025-05-05 |  |  |  |  | 2025-05-12 |  |  |  |  | 2025-05-19 |  |  |  |  | 2025-05-26 |  |  |  |  | 2025-06-02
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Analisis Kebutuhan | Ignasia, Wenanda , Hiskia | 2025-03-17 | 2025-04-03 | 17 |  | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3
1.1 | Analisis Kebutuhan Pengguna | Ignasia P. D. Kafiar | 2025-03-17 | 2025-03-19 | 2 | 100% | bar: 17 to 19
1.1.1 | Pengumpulan informasi tentang masalah pemilihan SMA |  | 2025-03-19 | 2025-03-20 | 1 | 100% | bar: 19 to 20
1.2 | Analisis Fungsional | Wenanda Nunuela | 2025-03-20 | 2025-03-23 | 3 | 100% | bar: 20 to 21
1.2.1 | Identifikasi Fitur Utama |  | 2025-03-23 | 2025-03-24 | 1 | 100% | bar: 24
1.2.2 | Penyusunan Use Case |  | 2025-03-24 | 2025-03-25 | 1 | 100% | bar: 24 to 25
1.2.3 | Validasi Kebutuhan Fungsional |  | 2025-03-25 | 2025-03-26 | 1 | 100% | bar: 25 to 26
1.3 | Analisis Non Fungsional | Hiskia | 2025-03-26 | 2025-03-30 | 4 | 100% | bar: 26 to 28
1.3.1 | Kebutuhan Performa |  | 2025-03-30 | 2025-03-31 | 1 | 100% | bar: 31
1.3.2 | Kebutuhan Keamanan |  | 2025-03-31 | 2025-04-01 | 1 | 100% | bar: 31 to 1
1.3.3 | Kebutuhan Usability |  | 2025-04-01 | 2025-04-02 | 1 | 100% | bar: 1 to 2
1.3.4 | Kebutuhan Keamanan |  | 2025-04-02 | 2025-04-03 | 1 | 100% | bar: 2 to 3
2 | Design | Anggy Alfatika Riyadi | 2025-04-03 | 2025-04-21 | 18
2.1 | Design Arsitektur Sistem |  | 2025-04-03 | 2025-04-07 | 4 | 100% | bar: 3 to 7
2.2 | Design Basis Data |  | 2025-04-07 | 2025-04-11 | 4 | 100% | bar: 7 to 11
2.3 | Desain Antarmuka Pengguna (UI Design) | Anggy Alfatika Riyadi | 2025-04-11 | 2025-04-15 | 4 | 100% | bar: 11 to 15
2.4 | Desain Interaksi & Navigasi |  | 2025-04-15 | 2025-04-17 | 2 | 100% | bar: 15 to 17
2.5 | Desain Keamanan Sistem |  | 2025-04-17 | 2025-04-19 | 2 | 100% | bar: 17 to 21
2.6 | Desain Responsif & Aksesibilitas |  | 2025-04-19 | 2025-04-21 | 2 | 100% | bar: 21 to 22
3 | Development |  | 2025-04-21 | 2025-05-12 | 21
3.1 | Persiapan Lingkungan Pengembangan | Nur Astin Prabansari | 2025-04-21 | 2025-04-25 | 4 | 100% | bar: 21 to 25
3.2 | Pengembangan Front-End |  | 2025-04-25 | 2025-04-30 | 5 | 100% | bar: 25 to 30
3.3 | Pengembangan Back-End | Grace Anastasya Liunokas | 2025-04-30 | 2025-05-04 | 4 | 100% | bar: 30 to 2
3.4 | Integrasi Frontend dan Backend |  | 2025-05-04 | 2025-05-08 | 4 | 100% | bar: 5 to 8
3.5 | Pengujian Fungsional (Unit Testing) |  | 2025-05-08 | 2025-05-10 | 2 | 100% | bar: 8 to 12
3.6 | Penanganan Error dan Validasi |  | 2025-05-10 | 2025-05-12 | 2 | 100% | bar: 9 to 12
4 | Testing |  | 2025-05-13 | 2025-05-20 | 7
4.1 | Perencanaan Pengujian | Chesia J Bless | 2025-05-13 | 2025-05-14 | 1 | 100% | bar: 12 to 14
4.2 | Unit Testing (Pengujian Modul) |  | 2025-05-14 | 2025-05-15 | 1 | 100% | bar: 14 to 15
4.3 | Integration Testing (Pengujian Antar Modul) |  | 2025-05-15 | 2025-05-18 | 3 | 100% | bar: 15 to 19
4.4 | UI/UX Testing (Pengujian Antarmuka) |  | 2025-05-18 | 2025-05-19 | 1 | 100% | bar: 16 to 19
4.5 | Validasi & Penanganan Error | Yolanda Andriani Homer | 2025-05-19 | 2025-05-20 | 1 | 100% | bar: 19 to 20
4.4 | Deployment |  | 2025-05-22 | 2025-06-03 | 12
4.5 | Persiapan Server | Angelica A N Rachmaitah | 2025-05-22 | 2025-05-25 | 3 | 100% | bar: 22 to 27
4.6 | Konfigurasi Aplikasi |  | 2025-05-25 | 2025-05-28 | 3 | 100% | bar: 27 to 29
4.7 | Final Testing di Server (Smoke Test) |  | 2025-05-28 | 2025-05-31 | 3 | 100% | bar: 28 to 2
4.5 | Backup & Keamanan |  | 2025-05-31 | 2025-06-03 | 3 | 100% | bar: 30 to 3
Formulas:
DATE = [DATE, row below]
DATE = [DATE]+2